Microsoft 365 Zero Trust Implementation Project Plan & Technical Reference Prepared by Versetal Audience: IT Administration Team Classification: Confidential Version 1.0

Section 1: Project Overview

This document provides the full implementation plan for deploying a Zero Trust security model across Microsoft 365. It is organized into four sequential phases spanning 16 weeks, with task-level detail, ownership assignments, licensing requirements, and success criteria for each phase.

| Phase | Name | Key Activities | Duration |
| --- | --- | --- | --- |
| 1 | Identity Hardening | MFA enforcement, legacy auth block, PIM, Conditional Access baseline, Entra ID Protection | Weeks 1–4 |
| 2 | Device Compliance | Intune compliance policies, WHfB, ASR rules, Defender for Endpoint, Autopilot | Weeks 5–8 |
| 3 | Data Protection & App Sec | Sensitivity labels, DLP, Defender for Cloud Apps (MCAS), MAM policies | Weeks 9–12 |
| 4 | Monitoring & Response | Sentinel SIEM, UEBA, analytics rules, IR runbooks, access reviews, tabletop exercise | Weeks 13–16 |

Before beginning any phase, create two break-glass emergency access accounts and confirm they are excluded from all Conditional Access policies. Test authentication for both accounts. Store credentials in a physically secured location offline. Failure to do this before Phase 1 can result in a complete tenant lockout.

| 1 | Foundation & Identity Hardening Weeks 1–4 |
| --- | --- |

Phase 1 establishes the security foundation. Identity is the primary control plane in a cloud-first environment. This phase ensures every account is verified before any access is permitted and eliminates the attack vectors most commonly exploited in M365 breaches.

Objectives

- Enforce MFA for all users via Conditional Access — not legacy per-user MFA

- Block all legacy authentication protocols that bypass MFA enforcement

- Deploy Privileged Identity Management (PIM) to eliminate standing admin access

- Establish the full Conditional Access baseline policy stack

- Enforce phishing-resistant MFA (FIDO2 / Windows Hello) for all admin accounts

- Activate Entra ID Protection sign-in and user risk policies

Task Plan

| Task | Owner | Week | License |
| --- | --- | --- | --- |
| Audit all admin accounts — remove any standing Global Administrator assignments | IT Admin | 1 | Any |
| Create two break-glass accounts and exclude from all CA policies | IT Admin | 1 | Any |
| Enable PIM for all privileged Entra ID roles (GA, PA, SA, CA, etc.) | IT Admin | 1 | AAD P2 |
| Deploy SSPR and Combined Registration for all users | IT Admin | 1 | AAD P1 |
| Define Named Locations (trusted office IPs, VPN egress) | IT Admin | 1 | Any |
| Deploy CA001 – Require MFA for all users (Report-only) | IT Admin | 2 | AAD P1 |
| Deploy CA002 – Block legacy authentication (Report-only) | IT Admin | 2 | AAD P1 |
| Deploy CA003 – Phishing-resistant MFA for admins (Report-only) | IT Admin | 2 | AAD P1 |
| Deploy CA008 – MFA from untrusted locations (Report-only) | IT Admin | 2 | AAD P1 |
| Deploy CA009 – MFA for Azure management (Report-only) | IT Admin | 2 | AAD P1 |
| Audit legacy auth sign-in logs — identify SMTP/IMAP/POP usage | IT Admin | 2–3 | Any |
| Migrate or document all legacy auth exceptions | IT Admin | 3 | Any |
| Enable CA002 (legacy auth block) after audit is clear | IT Admin | 3 | AAD P1 |
| Deploy CA004 – Block high-risk sign-ins (Report-only) | IT Admin | 3 | AAD P2 |
| Deploy CA005 – Require password change for high-risk users (Report-only) | IT Admin | 3 | AAD P2 |
| Enable CA001, CA003, CA008, CA009 after 14-day report-only review | IT Admin | 4 | AAD P1 |
| Enable CA004 and CA005 after reviewing false positive rate | IT Admin | 4 | AAD P2 |
| Review sign-in logs, validate policy impact, document exceptions | IT Admin | 4 | Any |

Success Criteria

- Zero standing Global Administrator accounts — all privileged access via PIM

- 100% of users covered by MFA Conditional Access policy (CA001 enabled)

- Legacy authentication blocked — Sign-in logs show zero successful legacy auth

- Entra ID Protection risk policies (CA004/CA005) active and generating alerts

| 2 | Device Compliance & Endpoint Security Weeks 5–8 |
| --- | --- |

Phase 2 extends Zero Trust to the device layer. A verified identity on a compromised or unmanaged device still represents significant risk. Intune compliance policies, tied to Conditional Access, ensure only healthy, managed devices can access corporate data.

Objectives

- Define and deploy Intune device compliance policies for Windows and mobile platforms

- Enforce device compliance as a Conditional Access grant control for all cloud apps

- Deploy Windows Hello for Business as the primary passwordless authentication method

- Configure Attack Surface Reduction rules via Intune security baselines

- Deploy Microsoft Defender for Endpoint with Intune integration

- Implement Autopilot enrollment for new device provisioning

Task Plan

| Task | Owner | Week | License |
| --- | --- | --- | --- |
| Define Windows compliance policy: BitLocker, Secure Boot, OS version, Defender AV | IT Admin | 5 | Intune P1 |
| Define iOS/Android compliance policy: OS version, PIN, encryption, jailbreak detection | IT Admin | 5 | Intune P1 |
| Enroll existing Windows devices into Intune (GPO MDM enrollment or co-management) | IT Admin | 5–6 | Intune P1 |
| Configure Autopilot profile and deployment profile for net-new device provisioning | IT Admin | 6 | Intune P1 |
| Deploy Windows Hello for Business policy via Intune | IT Admin | 6 | AAD P1 |
| Enable Microsoft Defender for Endpoint + Intune integration | IT Admin | 7 | MDE P1 |
| Deploy ASR rules via Intune — Audit mode first, then Enforce after 1-week review | IT Admin | 7 | MDE P1 |
| Deploy CA006 – Require compliant device for cloud apps (Report-only) | IT Admin | 7 | Intune |
| Deploy CA007 – App protection policy for mobile (Report-only) | IT Admin | 7 | Intune APP |
| Remediate all non-compliant devices — document any approved exceptions | IT Admin | 8 | Any |
| Enable CA006 and CA007 after confirming all devices enrolled and compliant | IT Admin | 8 | Intune |

Success Criteria

- All corporate Windows devices enrolled in Intune and reporting Compliant status

- CA006 enabled — unmanaged device access blocked to all M365 cloud apps

- Windows Hello for Business deployed and active on enrolled Windows endpoints

- ASR rules in Enforce mode with Defender for Endpoint alert baseline established

| 3 | Data Protection & Application Security Weeks 9–12 |
| --- | --- |

Phase 3 protects the data itself. Even with strong identity and device controls, data must be protected at the layer where it lives — in SharePoint, Teams, OneDrive, email, and connected SaaS applications.

Objectives

- Deploy Microsoft Purview sensitivity labels across all M365 workloads

- Configure Data Loss Prevention policies covering PII, PHI, and financial data

- Deploy Defender for Cloud Apps for shadow IT discovery and session controls

- Configure App Protection Policies for BYOD mobile devices (MAM-WE)

- Audit external sharing settings across SharePoint and Teams

Task Plan

| Task | Owner | Week | License |
| --- | --- | --- | --- |
| Design sensitivity label taxonomy: Public, Internal, Confidential, Highly Confidential | IT Admin | 9 | Purview P1 |
| Deploy sensitivity labels to M365 Apps, SharePoint, Teams, Exchange Online | IT Admin | 9–10 | Purview P1 |
| Configure auto-labeling policies for known sensitive data types (SSN, MRN, CC) | IT Admin | 10 | Purview P2 |
| Build DLP policy: block PII/PHI sharing externally via email and SharePoint | IT Admin | 10 | Purview P1 |
| Build DLP policy: alert on bulk SharePoint/OneDrive download activity | IT Admin | 10 | Purview P1 |
| Enable Defender for Cloud Apps connector for M365 | IT Admin | 11 | MDCA |
| Configure MCAS session policy: block download on unmanaged devices | IT Admin | 11 | MDCA |
| Configure MCAS shadow IT discovery and app governance dashboard | IT Admin | 11 | MDCA |
| Deploy Intune App Protection Policies for iOS/Android (Outlook, Teams, OneDrive) | IT Admin | 12 | Intune P1 |
| Audit SharePoint Admin Center external sharing settings — tighten to org-only where possible | IT Admin | 12 | Any |
| Deploy CA010 – Session controls for unmanaged devices (Report-only) | IT Admin | 12 | MDCA |

Success Criteria

- All M365 workloads covered by sensitivity labels with default labeling policy active

- DLP policies active and generating actionable alerts (not audit-only mode)

- MCAS blocking file downloads to unmanaged devices in browser sessions

- BYOD mobile devices managed via MAM with PIN enforcement and selective wipe capability

| 4 | Monitoring, Alerting & Continuous Improvement Weeks 13–16 |
| --- | --- |

Phase 4 operationalizes the security posture. Technology controls alone are insufficient — the organization needs visibility, alerting, and documented response processes to sustain Zero Trust over time.

Objectives

- Deploy and configure Microsoft Sentinel as the primary SIEM

- Connect all M365 and Entra ID data connectors to Sentinel

- Define and activate analytics rules for key threat scenarios

- Establish a Secure Score review cadence and remediation ownership process

- Document Incident Response runbooks for identity and data breach scenarios

- Conduct tabletop exercise and complete first privileged access review

Task Plan

| Task | Owner | Week | License |
| --- | --- | --- | --- |
| Deploy Microsoft Sentinel workspace — configure Log Analytics retention | IT Admin | 13 | Sentinel |
| Connect M365 Defender, Entra ID, Intune, Azure Activity data connectors | IT Admin | 13 | Sentinel |
| Enable Entra ID Protection analytics rules in Sentinel | IT Admin | 14 | AAD P2 |
| Enable UEBA (User Entity Behavior Analytics) in Sentinel | IT Admin | 14 | Sentinel |
| Deploy analytics rules: impossible travel, MFA fatigue, bulk download, new admin role | IT Admin | 14 | Sentinel |
| Configure automation playbooks (Logic Apps): auto-disable risky user on High risk | IT Admin | 15 | Sentinel |
| Enable CA010 (MCAS session controls) after MCAS session policy confirmed | IT Admin | 15 | MDCA |
| Establish monthly Secure Score review cadence with assigned remediation owners | IT Admin | 15 | Any |
| Document IR runbooks: compromised account, data exfiltration, ransomware | IT Admin | 15 | Any |
| Conduct Entra ID Access Review for all privileged roles | IT Admin | 16 | AAD P2 |
| Tabletop exercise: simulate BEC scenario — detection, containment, recovery | IT Admin | 16 | Any |
| 16-week implementation review — measure against Secure Score baseline | IT Admin | 16 | Any |

Success Criteria

- Sentinel receiving logs from all M365, Entra ID, Intune, and Defender data sources

- Minimum 5 analytics rules active with confirmed alert generation in test scenarios

- Incident Response runbooks documented and reviewed by relevant stakeholders

- Microsoft Secure Score above 70% in Defender portal

- First privileged role access review completed and certified

Section 2: Conditional Access Policy Stack

The following Conditional Access policies form the enforcement engine of this Zero Trust implementation. All policies are deployed via the Microsoft Graph API using the accompanying PowerShell script. Every policy should be deployed in Report-only mode, reviewed for 7–14 days, then switched to Enabled in the recommended sequence.

Always maintain break-glass accounts excluded from every policy. Deploy in Report-only first. Enable CA002 (legacy auth block) before enabling any other policy.

| Policy | Applies To | Requirement | Rationale |
| --- | --- | --- | --- |
| CA001 – MFA for all users | All users | MFA on every sign-in | Baseline MFA blocks >99.9% of automated credential attacks. |
| CA002 – Block legacy authentication | All users | Block legacy auth clients | IMAP/POP/SMTP AUTH cannot enforce MFA. Must be eliminated. |
| CA003 – Phishing-resistant MFA for admins | Privileged roles | FIDO2 or WHfB only | Standard MFA is phishable. Admins need hardware-bound auth. |
| CA004 – Block high-risk sign-ins | All users | Block if sign-in risk = High | ML-detected threats blocked in real time. Requires P2. |
| CA005 – Password change for high-risk users | All users | MFA + password change if user = High | Forces credential rotation when leaked creds are detected. P2. |
| CA006 – Require compliant device | All users, Windows/macOS | Intune-compliant or Entra-joined | Unmanaged devices are uncontrolled risk. |
| CA007 – App protection for mobile | All users, iOS/Android | Approved app + MAM policy | BYOD data protection without full device enrollment. |
| CA008 – MFA from untrusted locations | All users | MFA outside Named Locations | Location-aware risk. Adds friction from unknown networks. |
| CA009 – MFA for Azure management | All users | MFA for Azure portal/ARM/CLI | Azure management plane always protected independently. |
| CA010 – Session controls (MCAS) | All users, browser | MCAS proxy — no download/print | Allows unmanaged device access but prevents data exfiltration. |

Section 3: Risk Register

The following risks have been identified for this implementation. Each is assessed for likelihood and impact, with a defined mitigation strategy. This register should be reviewed at the start of each phase.

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| MFA rollout causes user lockout | Medium | High | Deploy Report-only first. Pre-communicate 2 weeks ahead. Maintain break-glass accounts. |
| Legacy apps break when legacy auth is blocked | Medium | Medium | Audit legacy auth usage in Sign-in logs before blocking. Create time-limited exceptions. |
| Non-compliant devices lose access pre-remediation | High | Medium | Run 7-day compliance grace period. Prioritize enrollment before enabling CA006. |
| Break-glass accounts not maintained or tested | Low | Critical | Test break-glass access quarterly. Alert on any sign-in. Store offline. |
| PIM activation delays for urgent admin tasks | Medium | Low | Set activation window to 4–8 hours. Allow self-approval for lower-sensitivity roles. |
| Sentinel ingestion cost overrun | Medium | Medium | Set data cap. Scope to security tables only (SigninLogs, AuditLogs, AlertInfo). |
| CA policy misconfiguration blocks all users | Low | Critical | Always test in Report-only mode. Never enable a block-all policy without break-glass exclusion. |

Section 4: Governance & Ongoing Management

Operational Cadence

| Frequency | Activity | Owner |
| --- | --- | --- |
| Weekly | Review Entra ID Protection risky users and sign-in risk alerts | IT Admin |
| Weekly | Review Secure Score delta and action new recommendations | IT Admin |
| Monthly | Privileged role access review (Entra Access Reviews) | IT Admin / Management |
| Monthly | Review CA policy change log — validate no unauthorized modifications | IT Admin |
| Quarterly | Full Conditional Access policy audit and re-validation | IT Admin |
| Quarterly | DLP policy review — tune for false positives and new data types | IT Admin |
| Quarterly | Penetration test or adversarial tabletop exercise | External / Internal |
| Annually | Zero Trust maturity assessment against Microsoft ZT framework | IT Admin |

Break-Glass Account Requirements

Two emergency access accounts must be maintained for the lifetime of this implementation. These are the only accounts excluded from all Conditional Access policies.

- Use a naming convention that clearly identifies them as emergency accounts

- Store credentials in a physically secured, offline location — not a password manager

- Exclude from all CA policies, PIM assignments, and MFA requirements

- Configure a Sentinel alert to immediately notify on any sign-in by these accounts

- Test quarterly — confirm they can authenticate to portal.azure.com

- Never use for day-to-day administration

Microsoft explicitly requires break-glass accounts before enabling any Conditional Access policy. A tenant lockout with no break-glass accounts has no self-service recovery path — only a Microsoft Support escalation, which can take 24–72 hours.