## Zero Trust Gantt
VERSETAL ¦ Microsoft 365 Zero Trust Implementation — Project Gantt Chart
16-Week Implementation ¦ All phases in sequence |  |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
Phase | Task / Activity | Owner | License Req. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
|  |  |  | Phase 1: Identity Hardening |  |  |  | Phase 2: Device Compliance |  |  |  | Phase 3: Data Protection |  |  |  | Phase 4: Monitoring & Response
Phase 1 | PHASE 1: FOUNDATION & IDENTITY HARDENING
1 | ▸ Create break-glass accounts & validate | IT Admin | Any
1 | ▸ Audit admin accounts — remove standing GA roles | IT Admin | Any | bar: Wk 1 1
1 | ▸ Enable PIM for all privileged Entra ID roles | IT Admin | AAD P2
1 | ▸ Deploy SSPR + Combined MFA Registration | IT Admin | AAD P1 | bar: Wk 1 1
1 | ▸ Define Named Locations (trusted IPs / VPN) | IT Admin | Any
1 | ▸ Deploy CA001–CA003, CA008, CA009 (Report-only) | IT Admin | AAD P1 | bar: Wk 2 2
1 | ▸ Audit legacy auth usage in Sign-in logs | IT Admin | Any
1 | ▸ Migrate / document legacy auth exceptions | IT Admin | Any | bar: Wk 3 3
1 | ◆ Enable CA002 — Block legacy authentication | IT Admin | AAD P1 | bar: Wk 1 1 to Wk 16 16
1 | ▸ Deploy CA004 & CA005 — Risk policies (Report-only) | IT Admin | AAD P2 | bar: Wk 3 3
1 | ◆ Enable CA001, CA003, CA008, CA009 | IT Admin | AAD P1 | bar: Wk 1 1 to Wk 16 16
1 | ◆ Enable CA004 & CA005 — Risk-based policies | IT Admin | AAD P2 | bar: Wk 4 4
1 | ▸ Phase 1 review — validate sign-in logs | IT Admin | Any
Phase 2 | PHASE 2: DEVICE COMPLIANCE & ENDPOINT SECURITY
2 | ▸ Define Windows compliance policy (BitLocker, Defender, OS) | IT Admin | Intune
2 | ▸ Define iOS/Android compliance policy | IT Admin | Intune | bar: Wk 5 5
2 | ▸ Enroll existing Windows devices into Intune | IT Admin | Intune
2 | ▸ Configure Autopilot profile for new devices | IT Admin | Intune | bar: Wk 6 6
2 | ▸ Deploy Windows Hello for Business via Intune | IT Admin | AAD P1
2 | ▸ Enable Defender for Endpoint + Intune integration | IT Admin | MDE P1 | bar: Wk 7 7
2 | ▸ Deploy ASR rules — Audit mode then Enforce | IT Admin | MDE P1
2 | ▸ Deploy CA006 & CA007 (Report-only) | IT Admin | Intune | bar: Wk 7 7
2 | ▸ Remediate non-compliant devices | IT Admin | Any
2 | ◆ Enable CA006 & CA007 — Device compliance enforced | IT Admin | Intune | bar: Wk 8 8
2 | ▸ Phase 2 review — validate device compliance status | IT Admin | Any
Phase 3 | PHASE 3: DATA PROTECTION & APP SECURITY
3 | ▸ Design sensitivity label taxonomy | IT Admin | Purview P1
3 | ▸ Deploy sensitivity labels across M365 workloads | IT Admin | Purview P1 | bar: Wk 9 9 to Wk 10 10
3 | ▸ Configure auto-labeling for known sensitive data types | IT Admin | Purview P2
3 | ▸ Build DLP policies — PII/PHI, bulk download alerts | IT Admin | Purview P1 | bar: Wk 10 10
3 | ▸ Enable Defender for Cloud Apps (MCAS) connector | IT Admin | MDCA
3 | ▸ Configure MCAS session policy — block download | IT Admin | MDCA | bar: Wk 11 11
3 | ▸ MCAS shadow IT discovery & app governance | IT Admin | MDCA
3 | ▸ Deploy Intune App Protection Policies (iOS/Android) | IT Admin | Intune | bar: Wk 12 12
3 | ▸ Audit SharePoint external sharing settings | IT Admin | Any
3 | ▸ Deploy CA010 — Session controls (Report-only) | IT Admin | MDCA | bar: Wk 12 12
3 | ▸ Phase 3 review — DLP alerts & label coverage | IT Admin | Any
Phase 4 | PHASE 4: MONITORING, ALERTING & RESPONSE
4 | ▸ Deploy Microsoft Sentinel workspace | IT Admin | Sentinel
4 | ▸ Connect M365 / Entra ID / Intune / Defender connectors | IT Admin | Sentinel | bar: Wk 13 13
4 | ▸ Enable Entra ID Protection analytics rules in Sentinel | IT Admin | AAD P2
4 | ▸ Enable UEBA in Sentinel | IT Admin | Sentinel | bar: Wk 14 14
4 | ▸ Deploy analytics rules (impossible travel, MFA fatigue, bulk DL) | IT Admin | Sentinel
4 | ▸ Configure Logic App playbooks — auto-disable risky user | IT Admin | Sentinel | bar: Wk 15 15
4 | ◆ Enable CA010 — MCAS session controls | IT Admin | MDCA | bar: Wk 1 1 to Wk 16 16
4 | ▸ Establish Secure Score monthly review cadence | IT Admin | Any | bar: Wk 15 15
4 | ▸ Document IR runbooks — BEC, exfil, ransomware | IT Admin | Any
4 | ▸ Conduct Entra ID Access Review (privileged roles) | IT Admin | AAD P2 | bar: Wk 16 16
4 | ▸ Tabletop exercise — BEC scenario simulation | IT Admin | Any
4 | ◆ 16-week implementation review & Secure Score baseline | IT Admin | Any | bar: Wk 16 16
Legend: |  |  |  | Wk 1 1: Phase 1; Wk 4 4: Phase 2; Wk 7 7: Phase 3; Wk 10 10: Phase 4; Wk 13 13: ◆ Milestone / Enable
License key: AAD P1 = Entra ID P1 (M365 Business Premium / E3) AAD P2 = Entra ID P2 (M365 E5 / add-on) MDE = Defender for Endpoint MDCA = Defender for Cloud Apps Sentinel = Microsoft Sentinel (pay-per-use)