Versetal Information Systems

Entra ID Migration Project Plan

On-Premises Active Directory Decommission & Cloud-Only Identity Migration

| Document Owner | Chris Sorel — Sr. Systems/Cloud Engineer |
| --- | --- |
| Reviewed By | Stacey Fernandes — CTO |
| Classification | Confidential — Internal Use Only |
| Version | 1.0 — Draft |

# 1. Project Overview

This document outlines the full project plan for migrating Versetal Information Systems from on-premises Active Directory (AD) to a cloud-only identity model using Microsoft Entra ID (formerly Azure AD). The goal is to decommission all on-premises Domain Controllers and Entra Connect, making Entra ID the sole identity authority across the organization.

Versetal is well-positioned for this migration. There are no domain-joined workstations or servers, all users are on Microsoft 365, and the user base is under 200 accounts. The estimated total effort is 12–21 hours of engineering work across a 2–3 day execution window with one planned maintenance window for the Entra Connect cutover.

## Key Assumptions

- No workstations or servers are domain-joined to on-premises AD

- All users are licensed on Microsoft 365 with Exchange Online

- Entra Connect (Azure AD Connect) is currently running Password Hash Sync (PHS)

- Entra ID tenant is already established and verified for versetalinfo.com

- PIM is already configured in Entra ID for privileged role management

## Success Criteria

- All on-premises Domain Controllers decommissioned

- Entra Connect decommissioned with no sync dependencies remaining

- All user objects converted to cloud-only identities

- All applications and services authenticating against Entra ID, not on-prem AD

- Dynamic groups and distribution lists functioning correctly post-migration

- No user authentication disruptions during or after cutover

# 2. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Application with undiscovered LDAP/Kerberos dependency | Medium | High | Pre-migration LDAP audit on all DCs using network capture + Event ID 2889 |
| Password hash sync incomplete at cutover | Low | High | Verify PHS health in Entra Connect Health dashboard before proceeding |
| User sign-in disruption during Entra Connect decommission | Low | High | Perform cutover during off-hours maintenance window; validate with test accounts first |
| Admin account access lost post-migration | Low | High | Verify break-glass accounts are cloud-only and working before decommissioning DCs |
| extensionAttribute1 lost after Entra Connect removed | Medium | Medium | Migrate Privileged flag to Entra Custom Security Attribute before decommissioning sync |
| DNS resolution failures after DC removal | Medium | Medium | Audit internal DNS zones; migrate any needed records to Azure DNS or internal forwarders |

# 3. Project Phases

Run Phase 1 and Phase 2 fully before touching any Domain Controller or Entra Connect configuration. The discovery and pre-flight phases are critical to avoiding unplanned outages.

## Phase 1 — Discovery & Dependency Audit

Estimated effort: 4–6 hours

The primary objective of this phase is to identify any applications, services, or infrastructure components that authenticate against or query on-premises Active Directory. Undiscovered dependencies are the leading cause of outages during DC decommissions.

| Step | Task | Owner |
| --- | --- | --- |
| 1.1 | Enable audit logging on all DCs: Event ID 2889 (LDAP unsigned bind) and 1644 (LDAP query diagnostics). Let run for minimum 5 business days to capture all auth patterns. | Chris Sorel |
| 1.2 | Run netstat and network capture on each DC to identify active LDAP (389/636) and Kerberos (88) connections from non-DC sources. | Chris Sorel |
| 1.3 | Review IIS/application logs on any on-prem web servers for LDAP auth references. | Chris Sorel |
| 1.4 | Audit Entra Connect sync rules — document all attribute flows, filtering rules, and any custom sync configurations. | Chris Sorel |
| 1.5 | Identify all service accounts (spotlsvc, svc_rapid7, MSOL accounts) and map each to its consuming application. | Chris Sorel |
| 1.6 | Review Rapid7, ConnectWise RMM, and SentinelOne for any on-prem AD connector configurations. | Chris Sorel |
| 1.7 | Identify all DNS zones hosted on DCs. Document which are AD-integrated and which records are still in use. | Chris Sorel |
| 1.8 | Document current Fine-Grained Password Policies and Default Domain Password Policy. Note what needs to be replicated in Entra ID Password Protection. | Chris Sorel |
| 1.9 | Compile full dependency report. Go/No-Go review with Stacey before proceeding to Phase 2. | Chris Sorel / Stacey Fernandes |

## Phase 2 — Pre-Flight & Cloud Readiness

Estimated effort: 3–5 hours

Prepare the Entra ID environment for cloud-only operation before any on-premises changes are made. Nothing in this phase is destructive.

| Step | Task | Owner |
| --- | --- | --- |
| 2.1 | Verify Entra ID Password Hash Sync is healthy and all user password hashes are synchronized. Check Entra Connect Health dashboard — confirm no sync errors. | Chris Sorel |
| 2.2 | Confirm break-glass accounts (vers_azbtg01, vers_azbtg02) are cloud-only objects in Entra ID and are excluded from all Conditional Access policies. Test sign-in. | Chris Sorel |
| 2.3 | Create Entra ID Custom Security Attribute definition to replace extensionAttribute1. Attribute set: "Identity", Attribute: "AccountTier", values: Privileged / Standard. | Chris Sorel |
| 2.4 | Write and test PowerShell script to migrate all accounts with extensionAttribute1 = Privileged to the new Custom Security Attribute in Entra ID. Run in -WhatIf mode first. | Chris Sorel |
| 2.5 | Update all Entra ID dynamic group rules that reference extensionAttribute1 to reference the new Custom Security Attribute. Validate group memberships. | Chris Sorel |
| 2.6 | Configure Entra ID Password Protection with banned password list and smart lockout to replace on-prem password policy enforcement. | Chris Sorel |
| 2.7 | Verify all Conditional Access policies reference cloud group membership only — no on-prem group sync dependencies. | Chris Sorel |
| 2.8 | Confirm PIM eligible role assignments are cloud-only and will survive Entra Connect removal. | Chris Sorel |
| 2.9 | Test SSO and MFA for a representative sample of users (5–10) in each department to establish baseline before any changes. | Chris Sorel |

## Phase 3 — Application Migration

Estimated effort: 2–4 hours (variable based on Phase 1 findings)

Migrate any applications identified in Phase 1 that authenticate against on-premises AD. Each application needs to be moved to Entra ID app registration or an equivalent cloud auth method before proceeding.

| Step | Task | Owner |
| --- | --- | --- |
| 3.1 | For each application with an LDAP dependency discovered in Phase 1: create a corresponding Entra ID app registration with appropriate permissions. | Chris Sorel |
| 3.2 | Migrate Spotlight service account (spotlsvc) to Entra ID managed identity or service principal as appropriate. | Chris Sorel |
| 3.3 | Migrate Rapid7 AD connector to use Entra ID SCIM or Graph API integration. Verify asset discovery is unaffected. | Chris Sorel |
| 3.4 | Validate ConnectWise RMM has no on-prem AD sync dependency. If using AD-joined agent polling, migrate to cloud-based agent management. | Chris Sorel |
| 3.5 | Verify SentinelOne console is pulling identity data from Entra ID rather than on-prem AD. Update integration if needed. | Chris Sorel |
| 3.6 | Test all migrated application authentications end-to-end before proceeding. | Chris Sorel |

## Phase 4 — User Identity Conversion

Estimated effort: 2–3 hours

Convert all user objects from synced (on-prem managed) to cloud-only identities. This is a one-way operation and must be executed carefully.

IMPORTANT: Once a user is converted to a cloud-only identity, the on-prem AD object no longer controls that account. Do not perform this phase until Phases 1–3 are fully complete and validated.

| Step | Task | Owner |
| --- | --- | --- |
| 4.1 | Export full user list from Entra ID (all synced objects) as backup before conversion. Store offline. | Chris Sorel |
| 4.2 | Confirm Entra Connect is in Staging Mode — do not disable yet. This allows rollback if needed. | Chris Sorel |
| 4.3 | Convert user objects from synced to cloud-only using Microsoft's Convert-MsolDomainToStandard process or Graph API migration tooling. Process a pilot group of 5–10 users first. | Chris Sorel |
| 4.4 | Validate pilot users: test sign-in, MFA, M365 access, mailbox access, Teams, SharePoint. Confirm no loss of access. | Chris Sorel |
| 4.5 | Convert remaining user objects in batches. Validate each batch before proceeding. | Chris Sorel |
| 4.6 | Convert admin accounts (sorel7612sc, lopezh5589, etc.) to cloud-only Entra ID accounts. Re-assign PIM roles as needed. | Chris Sorel |
| 4.7 | Run full post-conversion validation: all users sign in successfully, dynamic groups populated correctly, distribution lists resolving. | Chris Sorel |

## Phase 5 — Entra Connect Decommission (Maintenance Window)

Estimated effort: 1–2 hours | Requires scheduled maintenance window

Schedule a maintenance window during off-hours. Notify all staff in advance. Duration: 2 hours with 1-hour buffer. Rollback plan: re-enable Entra Connect sync if issues are detected within the window.

| Step | Task | Owner |
| --- | --- | --- |
| 5.1 | Send maintenance window notification to all staff minimum 48 hours in advance. | Chris Sorel / Stacey Fernandes |
| 5.2 | Immediately before window: take snapshot/backup of Entra Connect server VM. | Chris Sorel |
| 5.3 | Stop Entra Connect sync scheduler: Set-ADSyncScheduler -SyncCycleEnabled $false. | Chris Sorel |
| 5.4 | Perform final manual sync cycle and confirm completion with no errors. | Chris Sorel |
| 5.5 | Disable Entra Connect sync. Monitor Entra ID for 15 minutes — verify no user objects are deleted or modified unexpectedly. | Chris Sorel |
| 5.6 | Validate 5 representative users can sign in and access M365 services. | Chris Sorel |
| 5.7 | Uninstall Entra Connect from the sync server. Decommission or repurpose the VM. | Chris Sorel |
| 5.8 | Remove MSOL_ service accounts from on-prem AD (these were created by Entra Connect and are now orphaned). | Chris Sorel |

## Phase 6 — Domain Controller Decommission

Estimated effort: 2–3 hours

With Entra Connect removed and all identities cloud-only, the Domain Controllers can be safely decommissioned. Follow the steps in order — do not skip AD metadata cleanup.

| Step | Task | Owner |
| --- | --- | --- |
| 6.1 | Seize all FSMO roles onto a single DC if not already consolidated. | Chris Sorel |
| 6.2 | Demote each non-FSMO DC gracefully using dcpromo / Remove-ADDSDomainController. Validate AD replication health after each demotion. | Chris Sorel |
| 6.3 | Demote the final (FSMO) DC last. This removes the domain entirely. | Chris Sorel |
| 6.4 | Clean up AD metadata using ntdsutil or Active Directory Sites and Services to remove any lingering DC objects. | Chris Sorel |
| 6.5 | Remove all DC DNS records from internal DNS zones. Update DNS forwarder configurations on UniFi UCG Max to point to external resolvers or Azure DNS. | Chris Sorel |
| 6.6 | Decommission or repurpose DC VMs on ESXi (hyper01.sorelcorp.com). | Chris Sorel |
| 6.7 | Revoke any remaining on-prem Kerberos or NTLM service tickets — allow natural expiration or force via gpupdate. | Chris Sorel |

## Phase 7 — Post-Migration Validation & Hardening

Estimated effort: 1–2 hours

| Step | Task | Owner |
| --- | --- | --- |
| 7.1 | Full user authentication sweep — validate sign-in for users in each country (US, India, Canada) and each employeeType category. | Chris Sorel |
| 7.2 | Validate all Entra ID dynamic groups have correct membership post-migration. Spot-check 3–5 groups per category. | Chris Sorel |
| 7.3 | Validate all dynamic distribution lists in Exchange Online are resolving correctly. | Chris Sorel |
| 7.4 | Confirm Custom Security Attribute (AccountTier = Privileged) is present on all admin accounts and Conditional Access exclusions are functioning. | Chris Sorel |
| 7.5 | Run Entra ID Secure Score assessment and address any new recommendations surfaced post-migration. | Chris Sorel |
| 7.6 | Update IT Glue / Hudu documentation to reflect cloud-only identity architecture. | Chris Sorel |
| 7.7 | Close out project — post-migration debrief with Stacey. Document lessons learned. | Chris Sorel / Stacey Fernandes |

# 4. Effort Summary

| Phase | Description | Effort | Notes |
| --- | --- | --- | --- |
| 1 | Discovery & Dependency Audit | 4–6 hours | Must run 5+ business days for LDAP audit |
| 2 | Pre-Flight & Cloud Readiness | 3–5 hours | Non-destructive |
| 3 | Application Migration | 2–4 hours | Variable on findings |
| 4 | User Identity Conversion | 2–3 hours | One-way operation |
| 5 | Entra Connect Decommission | 1–2 hours | Maintenance window required |
| 6 | Domain Controller Decommission | 2–3 hours | Final DC removed last |
| 7 | Validation & Hardening | 1–2 hours |  |
|  | TOTAL | 15–25 hours | ~2–3 day execution |

# 5. Key Contacts & References

| Name | Role | Notes |
| --- | --- | --- |
| Chris Sorel | Sr. Systems/Cloud Engineer | Project lead — all phases |
| Stacey Fernandes | CTO | Go/No-Go approvals, phase sign-offs |
| vers_azbtg01 | Break-glass Account 1 | OID: 1f24d999-5644-44a9-a79e-a6d2d83ec2e4 |
| vers_azbtg02 | Break-glass Account 2 | OID: 430380e1-b2c6-4d1f-a56b-0fc776839b1c |

This document should be reviewed and approved by Stacey Fernandes before Phase 1 begins. All Go/No-Go checkpoints require CTO sign-off before proceeding to the next phase.